## About
Project Name | Agile Manifesto and Methodologies
Users | Students
Created By | Instructor

## Epics and Features
Epic ID | Epic Name | Feature ID | Feature Name | Description
E1 | Create a web-based platform to educate and engage users about the Agile Manifesto and methodologies | F1 | Homepage for Agile Manifesto | Design and implement a homepage explaining the Agile Manifesto.
E1 | Create a web-based platform to educate and engage users about the Agile Manifesto and methodologies | F2 | Agile Values and Principles | Create interactive pages for Agile values and principles.
E1 | Create a web-based platform to educate and engage users about the Agile Manifesto and methodologies | F3 | Resource Library | Develop a library for Agile practices and resources.
E1 | Create a web-based platform to educate and engage users about the Agile Manifesto and methodologies | F4 | Collaboration Features | Implement collaboration features like forums and comments.

## User Stories
Story ID | Feature ID | User Story | Story Points | Sprint
S1.1 | F1 | Design and implement a visually appealing homepage. | 5 | 1
S1.2 | F1 | Add an introduction to Agile and its history. | 3 | 1
S1.3 | F1 | Include navigation to other sections of the platform. | 3 | 1
S2.1 | F2 | Create a page to display the four core Agile values. | 5 | 2
S2.2 | F2 | Implement an interactive feature to explain the 12 principles. | 8 | 2
S2.3 | F2 | Add examples to illustrate each value and principle. | 5 | 2
S3.1 | F3 | Design a library for Agile practices (Scrum, Kanban, etc.). | 5 | 3
S3.2 | F3 | Include downloadable resources like templates and guides. | 3 | 3
S3.3 | F3 | Add search and filter functionality. | 5 | 3
S4.1 | F4 | Develop a discussion forum for users. | 8 | 4
S4.2 | F4 | Enable users to comment on resources and principles. | 5 | 4
S4.3 | F4 | Implement user authentication for collaboration features. | 8 | 4

## Subtasks
Subtask ID | Story ID | Subtask Description | Assigned To | Status
ST1.1.1 | S1.1 | Create wireframes for the homepage. | Designer | To Do
ST1.1.2 | S1.1 | Develop HTML and CSS for the layout. | Developer | To Do
ST1.1.3 | S1.1 | Integrate animations using JavaScript. | Developer | To Do
ST1.1.4 | S1.1 | Conduct user testing and gather feedback. | Tester | To Do
ST4.2.1 | S4.2 | Design the comment input field and UI. | UI/UX Designer | To Do
ST4.2.2 | S4.2 | Develop backend APIs for storing comments. | Backend Developer | To Do
ST4.2.3 | S4.2 | Implement frontend integration with APIs. | Frontend Developer | To Do
ST4.2.4 | S4.2 | Test the comment functionality. | Tester | To Do

## Sprint Planning
Sprint Number | Start Date | End Date | User Stories Planned | Total Story Points
1 | 2025-01-08 | 2025-01-21 | S1.1, S1.2, S1.3 | 11
2 | 2025-01-22 | 2025-02-04 | S2.1, S2.2, S2.3 | 18
3 | 2025-02-05 | 2025-02-18 | S3.1, S3.2, S3.3 | 13
4 | 2025-02-19 | 2025-03-03 | S4.1, S4.2, S4.3 | 21